## 0.Revision history
0. Revision history
date | Ver. | Modified by | Modified Tap | modification item
2022-11-03 | 1.0.0 | DN Kim | ALL TAP | New (Prepared based on Samsung foundy's ZECH") _Digital

## 1 Design flow
1 IP Design flow
integration flow
sign-off check (mandatory)
sign-off check (optional)
design review
| Design Stage | What | How (Tool or Script) | Output | Who
1st S/O | Design Requirement & Specification | Design requirement acceptance | Document template | Design SOR | Analog design
|  | Design specification signed-off by all parties |  | Design information | Digital/Analog
|  | Production/bench test requirements (Functional & Scan) |  | Design note | Digital design
|  | Interface specification and requirements |  |  | Digital/Analog
|  | Architecture and block partitioning |  |  | Digital design
|  | Block diagram, specification and functional description |  |  | Digital design
|  | I/O and SFR list |  |  | Digital/Analog
|  | Initialization sequence |  |  | Analog
|  | Power-down mode sequence |  |  | Analog
|  | Clock/reset domain list & diagram |  |  | Digital design
|  | Simulation plan completed |  |  | Digital/Analog
▼
| RTL Design | Testable RTL design completed | Verilog | RTL | Digital design
|  | Detailed design documentation completed | MAKE_PHYD | Design note (doc/ppt) | Digital design
|  | SOR(Statement of Requirement) | Document template | Verification SOR | Digital design
|  |  |  | PMA top verilog model | Digital design
▼
| DFT | DFT rule checked and fault coverage estimation | SpyGlass-DFT | log file | Digital design
report file
| Lint | HDL syntax and structure issues checked by SEC RTL coding rule | SpyGlass-Lint | log file | Digital design
report file
waiver file (optional)
| CDC | Clock domain crossing checked | Meridian-CDC | report file | Digital design
|  | Waive list confirmed for CDC warnings |  | waiver file (optional)
|  | Logic block diagram and waive reason is described for all waive points |  | waiver review doc.
▼
| Function Simulation & Verification | Functional simulation completed | Verilog | Functional simulation lists & results | Digital design
|  | Test mode simulation completed | X-model | Test mode simulation lists & results | Digital design
|  | X-model simulation completed | UVM | X-model simulation lists & results | Digital design
|  | 100% code coverage for PMA digital |  | VerDict for PMA digital, not PCS | Design verification
|  | Full stack beta-DV completed |  | VerDict for PCS | Design verification
▼
| Architecture & RTL Design Review(DR1) | D-ZECH and Design note reviewed | DR | D-ZECH | Digital design
|  | All simulation results reviewed |  | Action item list | Digital design
|  | SOR and results reviewed |  |  | Digital design
|  | VerDict reviewed |  |  | Digital design
▼
| Logic Synthesis | SDC clean-up | GCA | report files | Digital design
|  | Logic synthesis completed | Design Compiler | check_design file
report files (timing, area …)
scan-ready netlist
▼
| DFT Insertion | Full scan design implementation completed | DFT Compiler | log file | Digital design
|  | - including core_wrapper |  | report files (drc, scan path …)
scan netlist
▼
| ATPG | ATPG(Stuck-at) completed and patterns verified | TetraMAX | log file | Digital design
report files (faults …)
ATPG vectors
| Equivalence Check (R2N) | Functional equivalence(function mode) of two designs(R2N*) proven | Formality | log file | Digital design
|  | * R2N = RTL to final netlist(pre-netlist) |  | report file (failing point, …)
| Pre-layout STA | Setup timing checked with pre-layout margin | PrimeTime | check_timing file | Digital design
report files (timing, violator, analysis …)
| Pre-layout Simulation | ATPG simulation completed | Verilog | log file | Digital design
Functional simulation completed (optional)
▼
P&R | P&R | RTL to GDS | ICC2 | post-layout netlist | Physical design
MDB
▼
2nd S/O | CDM(Charged Device Model) Check | Inserted CDM buffer checked | CDM checker | report file | Digital design
▼
| LVS/Spice netlist generation | LVS netlist generated for top LVS | Script | LVS netlist | Digital design
|  | Spice netlist generated for top simulation |  | Spice netlist
▼
| RC Extraction | RC extraction completed for the SPEF | Star-RCXT | SPEF files | Physical design
report file (*.star_sum)
| Equivalence Check (N2N) | Functional equivalence of two designs(N2N*) proven | Formality | log file | Digital design
|  | * N2N = final netlist(pre-netlist) to eco netlist(post-netlist) |  | report file (failing point, …)
| Post-layout STA | Static timing analysis completed and timing sign-off | PrimeTime | check_timing file | Digital design
|  | Final SDF extracted |  | update_timing file | (or Physical design)
report file (timing, violator, …)
SDF files
| ATPG | ATPG(All) completed and patterns verified | TetraMAX | log file | Digital design
report files (faults …)
ATPG vectors
| Post-layout Simulation | Dynamic simulation completed using post-layout SDF | Verilog | All simulation lists & results@D-ZECH | Digital design
| Static IR-Drop, DvD, Power/Signal EM | Static IR-drop, DvD and Power/Signal EM analysis completed | RedHawk | result files (*.log, *.rpt) | Physical design
▼
| 2nd Sign-off Design Review (DR2) | D-ZECH reviewed | DR | D-ZECH | Digital design
Action item list
▼
| DK Generation | Library | PrimeTime(ETM)/MAKE_LIB/LIB checker | .lib/.db | Digital design
|  | JTAG wrapper | Script | JTAG wrapper
|  | WGL | VTRAN | .wgl
|  | Model | Verilog | .v | Digital design
| Vector generation | ATE test simulation completed | Verilog |  | Digital design
|  | Vector generation completed | VectorGen (excel)

## 2 Changing
2 Changing summary
■ Customer:
■ IP Name:
■ Process:
Category | Sub Category | Modification description | Reason & Purpose | Estimated risk | Designer Name | Reviewer | Reviewer Comment | Details

## 3 IP Design checklist
3 IP Design check list | [8 empty] | Number | Percentage
[8 empty] | 완료 (OK) | 0 | 0%
[8 empty] | 웨이버 | 0 | 0%
|  |  | ■ Customer: |  |  |  |  | 미진행 | 105 | 100%
|  |  | ■ IP Name: |  |  |  |  | 해당사항없음 | 0 | 0%
|  |  | ■ Process: |  |  |  |  | 불충분 | 0 | 0%
[8 empty] | 진행중 | 0 | 0%
[8 empty] | 완료율 (%) | 0/105 | 0%
Category | Item | No | Check Point | Designer | Result / Evidence | Designer comment | Reviewer | Reviewer Comment | Check | Details
1. Documentation for Design Specification | Design SOR (.doc) | 1.1 | Detailed design requirements(i.e. design SOR) MUST be obtained from analog design team. Also, design SOR should contain detailed information for digital design. Specify EDM path of document. | [5 empty] | 미진행
| Design information (.xls) | 1.2 | Design information file MUST be cross-reviewed and generated by both digital and analog design team. Also, following contents MUST be included: . All SFR by control type and categorization . Analog/Digital Interface: Timing diagram of initialization sequence . Analog/Digital Interface: Timing diagram of transition between different power-down modes . Analog/Digital Interface: Analog control signal table @each power-down state . CPR information . List of ATB and DTB signals . Test items for ATE Specify EDM path of document. | [5 empty] | 미진행
| Design note (.doc) | 1.3 | Design note MUST be based on design SOR and following contents MUST be included: . All functional features and specifications including change list . Digital block diagram . Structure of clock distribution network . Reset structure diagram . Analog/Digital interface specification and timing diagram . PCS/PMA interface specification and timing diagram . BIST modes and supported patterns including programmable user pattern - PRBS and user-defined pattern should be available Specify EDM path of document. | [5 empty] | 미진행
| Noise scenario SOR (.doc) | 1.4 | Noise scenario SOR MUST be generated and delivered to PCS design team. It's very important to make robust design. Specify EDM path of document. | [5 empty] | 미진행
| Verification SOR (.doc) | 1.5 | Verification SOR MUST be generated and provided to design verification team. Specify EDM path of document. | [5 empty] | 미진행
| Test timing specification (.doc) | 1.6 | Interface timing specifications(e.g. clock frequency, data skew) regarding test modes MUST be provided to customer, and you should allow customer to reflect them on top-level design. . Reference clocks . APB interface . SCAN signals . JTAG signals Specify EDM path of document. | [5 empty] | 미진행
| PMA data sheet (.doc or .pdf) | 1.7 | Datasheet MUST be produced and include following items: . IP Specification . Pin description . Functional description . Register description . Programming guide Specify EDM path of document. | [5 empty] | 미진행
| PMA test guide (.doc or .pdf) | 1.8 | Test plan MUST be generated and following items MUST be included: . Test related pins . Test items . Vector generation guide . Test board guide Specify EDM path of document. | [5 empty] | 미진행
2. Static Quality Checks (LogCat) | HTML report generated | 2.1 | Specify the HTML file path of LogCat, hreport/index.html. | [5 empty] | 미진행
| Confirm 0 errors (including fatal) | 2.2 | Error MUST be cleared and cannot be waived. Provide the rule number and your comments for waiver if you have any custom rule violation(i.e. error and fatal). | [5 empty] | 미진행
| All LINT(SpyGlass-Lint) warnings reviewed and resolved | 2.3 | Review all warnings with waivers and confirm them. - Ensure to solve the warning level issues.(or at least aware of the potential problem.) - When you use the waivers to filter some violation messages of specified rules, you MUST review all waivers and confirm that. It's not possible to waive Error-MustFix even if waiver file has (Error-MustFix)rule names. | [5 empty] | 미진행
| All CDC(Meridian-CDC) waivers reviewed and documented as CDC Waivers | 2.4 | Confirm 0 error and 0 warning with waivers. - When you use the waivers to filter some violation messages of specified rules, you MUST review all waivers and confirm that. Also, you MUST provide a document for waiver if you waive some items. | [5 empty] | 미진행
| All SYN(Design-Compiler) warning reviewed and resolved | 2.5 | Confirm 0 errors and all warnings. - Ensure to solve the warning level issues.(or at least aware of the potential problem.) - Check if there is design(or lint) violation as following. . Timing loop . Multiple driver [Note] Linked material is just a reference, not for sign-off. | [5 empty] | 미진행
| All LEC(Formality) warning reviewed and resolved @pre-layout | 2.6 | Confirm 0 non-equivalent points and all warnings @function mode. - Ensure to solve the warning level issues.(or at least aware of the potential problem.) - You should check the functional equivalence between RTL and pre-layout netlist(R2N*), and all compare points MUST be passed verification. The functional equivalence should be checked by setting the functional mode before and after the scan insertion. *R2N: Comparison with RTL to pre-layout netlist(final synthesized netlist before P&R start) | [5 empty] | 미진행
| All CDM(CDM-Checker) warning reviewed and resolved | 2.7 | Confirm 0 errors and all warnings. - Ensure to solve the warning level issues.(or at least aware of the potential problem.) - Check if there is buffer insertion to the input net of CDM cell. | [5 empty] | 미진행
| All LEC(Formality) warning reviewed and resolved @post-layout | 2.8 | Confirm 0 non-equivalent points and all warnings @function and test mode - Ensure to solve the warning level issues.(or at least aware of the potential problem.) - You should check the functional equivalence with final post-layout netlist*(N2N) which is used for tape-out LVS, and all compare points MUST be passed verification. Where, pre-layout netlist should be confirmed at pre-layout LEC(R2N). * N2N: comparison with pre-layout netlist to final post-layout netlist | [5 empty] | 미진행
| All PEX(StarRC) warning reviewed and resolved | 2.9 | Confirm 0 errors and all warnings. - All error messages should be cleared regardless of error type - Following warning messages must be fixed before StarRC sign-off: . (EX-414): open net . (SX-0955): shorted nets . (SX-0957): fill shorts . Minimum spacing violations for layers . (EX0-212): Device terminal --> Polygon opens . Net out of scope - Other warning messages should be checked with StarRC support. | [5 empty] | 미진행
| All SDC(GCA) warning reviewed and resolved @post-layout | 2.10 | Confirm 0 errors and all warnings. - Ensure to solve the warning level issues.(or at least aware of the potential problem.) - Some clock rule violations are reported as warning. Confirm that especially all no_clock points are invalid. | [5 empty] | 미진행
| All STA(PrimeTime) warning reviewed and resolved @post-layout | 2.11 | Confirm 0 errors and all warnings including following points: . timing exception (e.g. set_false_path, set_multicycle_path) . no_clock . clock_gating . untested - Ensure to solve the warning level issues.(or at least aware of the potential problem.) - check_timing results check for potential timing problem due to design structure or constraint error. Hence, you should always perform check_timing and check the results whenever design changes or new constraints are added. | [5 empty] | 미진행
| All SIM(NC-Verilog) warning reviewed and resolved @post-layout | 2.12 | Confirm 0 errors and all warnings. - Ensure to solve the warning level issues.(or at least aware of the potential problem.) | [5 empty] | 미진행
| All ATPG(TetraMax) warning reviewed and resolved @post-layout | 2.13 | Confirm 0 errors and all warnings. - Ensure to solve the warning level issues.(or at least aware of the potential problem.) | [5 empty] | 미진행
| All SDC(GCA) warning reviewed and resolved @ETM | 2.14 | Confirm 0 errors and all warnings. - Ensure to solve the warning level issues.(or at least aware of the potential problem.) - Some clock rule violations are reported as warning. Confirm that especially all no_clock points are invalid. | [5 empty] | 미진행
| All ETM(PrimeTime) warning reviewed and resolved | 2.15 | Confirm 0 errors and all warnings. . timing exception (e.g. set_false_path, set_multicycle_path) . no_clock . clock_gating . untested - Ensure to solve the warning level issues.(or at least aware of the potential problem.) - check_timing results check for potential timing problem due to design structure or constraint error. Hence, you should always perform check_timing and check the results whenever design changes or new constraints are added. | [5 empty] | 미진행
| All information and setup_warning reviewed | 2.16 | Information level messages are not usually MUST-fix however they are useful to make robust design. | [5 empty] | 미진행
3. RTL Sign-off | All CDK's version checked | 3.1 | You MUST check whether the latest version is used if PMA digital logic has the CDK such as below: . EOM/FOM logic . Input offset calibration logic . CDR logic . SSLMS logic . PLL logic | [5 empty] | 미진행
| Tied to 0 with all output ports to analog block | 3.2 | All output signals to analog block MUST be tied to '0' in scan mode. Otherwise, it will cause electrical short between power and ground during ATE test such as SCAN and DVS(Dynamic Voltage Stress). | [5 empty] | 미진행
4. Logic Synthesis (Design Compiler) | Confirm APB clock frequency with customer | 4.1 | Specify confirmed APB clock frequency. The maximum APB clock frequency MUST be checked with customer because that frequency depends on the APB bus on the SOC(or ASIC) top-level. | [5 empty] | 미진행
5. Scan Insertion (DFT Compiler) | No errors in the log | 5.1 | Error MUST be cleared and cannot be waived. | [5 empty] | 미진행
| No DRC violation | 5.2 | DFT DRC rule violations MUST be fixed, and clock and reset of all the scan flip-flops MUST be directly controllable from the primary ports. Validate the following command report files as a part of the scan design rule check. . preview_dft: generates the scan architecture information implemented in the design . dft_drc: checks the current design against the test design rules of the test scan implementation | [5 empty] | 미진행
| DFT isolation ring(i.e. core wrapping) inserted | 5.3 | DFT isolation ring(i.e. core wrapping) MUST be inserted to allow functional core to be tested separately from other functional logics. During insertion, followings MUST be excluded: . Functional and test clock ports . Asynchronous set or reset signal ports . Scan-input, scan-output, scan-enable and other global test signal ports . Wrapper signal ports . Any port with a constant test signal value defined | [5 empty] | 미진행
| Length of scan chain < 250 FFs | 5.4 | Specify length of scan chain. You MUST meet the rules for scan chain length. - Assign scan chain length at around 200 (Num. close to 200 recommended; No num. greater than 300) | [5 empty] | 미진행
6. Pre-layout STA (PrimeTime) | No errors in the logs | 6.1 | Error MUST be cleared and cannot be waived. | [5 empty] | 미진행
| All warnings reviewed and resolved | 6.2 | Review all warnings and confirm them. - Ensure to solve the warning level issues.(or at least aware of the potential problem.) | [5 empty] | 미진행
| Confirm 0 setup timing violation | 6.3 | You MUST sign-off synthesized logic netlist for predictable timing closure. Make sure that following check items are satisfied at delay-worst corner of function mode. . No setup timing violation . No extraordinary big hold timing violation . No minimum period violation | [5 empty] | 미진행
7. Verification Coverage (DV) | RTL version reviewed | 7.1 | The primary DUT is PMA digital part. So, you MUST check whether RTL is the latest version. If there is version update, inform through DV JIRA so that the RTL of the latest version can always be used. - PMA analog will be verified only as an interoperability with PMA digital. | [5 empty] | 미진행
| PMA verilog model version reviewed | 7.2 | Specify verilog model version. You should check the version of PMA verilog model before releasing it to design verification team, and provide the latest verilog model. | [5 empty] | 미진행
| VerDict cross-reviewed with design verification team and signed-off ("Beta DV: PASS") | 7.3 | Specify EDM path of VerDict. Cross-review the VerDict sheet to check if there are any missing items between the design team and the verification team. If there are any deficiencies, supplement the test case. | [5 empty] | 미진행
| Function coverage 100% passing with waivers | 7.4 | Functional coverage is important to any verification approach since it is one of the factors used to determine when testing is done. Specifically, 100% functional coverage indicates that all items in the test plan have been tested. Combine this with 100% code coverage and it indicates that testing is done. | [5 empty] | 미진행
| Function coverage waivers reviewed and signed-off | 7.5 | Functional coverage is code that observes execution of a test plan. You MUST ensure that you have covered whole RTL and function features. | [5 empty] | 미진행
| Code coverage 100% with waivers | 7.6 | Test done = Test plan executed and All code executed Even if your code coverage is 100% you cannot say that your func cov. is 100% because there may be missing code in the RTL that was expected to be there according to the specification. | [5 empty] | 미진행
| Code coverage waivers reviewed and signed-off | 7.7 | There should be no exclude block and expression in the code coverage analysis. However, if the block and expression are excluded due to the lack of verification SOR or lack of verification scenarios, the item will eventually affect the function coverage. | [5 empty] | 미진행
| No RTL bugs | 7.8 | RTL bug was found in Beta-DV(or final DV), but RTL fix may not be made due to project schedule. In this case, it should be specified whether there is bug that are decided to be modified in the next project due to the known issue. Also, the JIRA issue should not be closed. | [5 empty] | 미진행
| All JIRA DV issues closed | 7.9 | At the time of Beta-DV(or final DV) completion, you MUST review if all JIRA issues have been closed. If the DV including both function and code coverage is completed but the JIRA issue is not closed, you cannot say that Beta-DV is completion. | [5 empty] | 미진행
8. P&R (ICC2) | SDC generated from pre-layout STA | 8.1 | You MUST provide to physical design team the SDC(i.e. timing constraints) exported from pre-layout STA stage because clean SDC should be used in P&R. The quality of SDC can make a tremendous impact on the P&R result and TAT. | [5 empty] | 미진행
| ECO and spare cell inserted | 8.2 | ECO and spare cell MUST be inserted and you MUST check whether they are inserted after P&R. - Whenever the design is required to perform some functional ECO, spare cell would be used. | [5 empty] | 미진행
| Clock path reviewed with physical design team | 8.3 | Insert shielding metals around clock nets and widening clocks net's width/space to prevent noise problem and timing performance degradation.(e.g. IP spec - 2w2s) Since the clock signal is one of the most important signal in a synchronized design, designer should efficiently prevent crosstalk noise on clock line. Clock shield is one of the efficient methods to prevent crosstalk. [Note] Linked material is just a reference, not for sign-off. | [5 empty] | 미진행
9. RC Extraction (StarRC) | Command file(i.e. run-set) version checked e.g.) LN04LPE_Cell_template_star.cmd | 9.1 | Command file is ASCII file containing StarRC commands that controls extraction functions. You MUST check whether it is the latest because those correct commands should be applied to StarRC flow. - Check the section PEX Commands for Cell Level Design of the sign-off document for each process. | [5 empty] | 미진행
| Metal stack option checked with analog design team | 9.2 | StarRC uses the NXTGRD file to calculate parasitics of the actual layout by pattern matching, and this database contain conductor sheet resistances and modules for 3D parasitic capacitance calculation. So, you MUST check top metal-stack option and then apply the NXTGRD file with matched metal-stack option during RC extraction. | [5 empty] | 미진행
| NXTGRD file version checked | 9.3 | The version of StarRC NXTGRD file MUST be matched the latest PDK version. | [5 empty] | 미진행
10. Timing Constraint Verification (GCA) | [for Serdes IP only] Timing requirements for serializer | 10.1 | Specify EDM path of document. You need the timing requirements for both serializer and deserializer in order to check interface timing correctly between digital and analog and they MUST be obtained from analog design team. Also, they may vary depending on process and design. . Serializer: set_output_delay -min/max DELAY [get_ports B] | [5 empty] | 미진행
| [for Serdes IP only] Timing requirements for deserializer | 10.2 | Specify EDM path of document. You need the timing requirements for both serializer and deserializer in order to check interface timing correctly between digital and analog and they MUST be obtained from analog design team. Also, they may vary depending on process and design. . Deserializer: set_input_delay -min/max DELAY [get_ports A] | [5 empty] | 미진행
| All supported STA scenarios defined and aligned with SDC | 10.3 | Specify each timing scenario according to the STA plan. You should establish STA plan to cover all meaningful timing path. [Example] normal, loopback, scan | [5 empty] | 미진행
11. Post-Layout STA (PrimeTime) | [for Vtyp±10% only] PrimeTime reference script's version reviewed | 11.1 | Specify version of script. You should check the version of PrimeTime reference script, which is customized by design technology team, and make sure to use the latest one. You can download this from B2B(or SmartD&E) system. | [5 empty] | 미진행
| [for Vtyp±10% only] Design spec. for OCV margin checked and reviewed with design technology team | 11.2 | To perform the accurate STA, you have to set proper OCV margin calculated by margin estimator. In case of foundry DM(e.g. Vtyp±10%), you MUST get the OCV margin from the margin estimation tool, AntsMaestro by design technology team and check the design conditions for inputs. [Note] Linked material is just a reference, not for sign-off. | [5 empty] | 미진행
| [for Vtyp±5% only] Excel based timing Margin Estimator(ME) version checked | 11.3 | Since the timing margin is very complicated and varies according to design specification, a margin estimator is provided to present the appropriate sign-off OCV timing margins according to the design specification. To get timing margins for each target process, use the excel sheet provided by design technology team. Design technology team release each maring estimator according to process. | [5 empty] | 미진행
| [for Vtyp±5% only] Design spec. for OCV margin calculation reviewed | 11.4 | You can choose each design condition according to the design specification. . Voltage . Temperature . Reliability margins | [5 empty] | 미진행
| STA sign-off corners checked and implemented | 11.5 | Ensure that timing sign-off corners for the final timing sign-off. The sign-off document provides the timing sign-off requirements such as sign-off criteria, RC extraction, timing sign-off corners, and timing sign-off margins. You can download this from the website, samsungfoundry. | [5 empty] | 미진행
| Version and option for SDF generation checked | 11.6 | You can check the SDF version through PrimeTime application note and the confirmed version should be specified when extracting the SDF. If the version does not match, the annotated timing is likely to be applied incorrectly during post-layout simulation. | [5 empty] | 미진행
12. Post-Layout Simulation (Verilog) | Post-layout netlist simulated with SDF annotation 100% at SS/FF corners | 12.1 | The SDF must be extracted for both worst and best corners that performed Post STA and the SDF must be annotated in the verilog simulation environment. | [5 empty] | 미진행
| Function mode tests 100% passing | 12.2 | You MUST check whether the simulation has been completed with annotation of the SDF in the verilog simulation environment. This function mode test can be performed in PCS full-stack simulation by design verification team. . APB read/wriete | [5 empty] | 미진행
| Test mode tests 100% passing | 12.3 | You MUST run the simulation for test modes such as following: . APB read/write . SCAN test with parallel and serial . External loopback with all supported BIST patterns . Internal loopback with all supported BIST patterns | [5 empty] | 미진행
| X-model test cases 100% passing | 12.4 | You MUST verify the function of following blocks with X-model and confirm that there is no problem. . EOM/FOM . Input offset calibration . SSLMS for DFE . CTLE adaptation | [5 empty] | 미진행
| Current-aware model test cases 100% passing | 12.5 | You MUST run the simulation for leakage current with current-aware model when powered-down. Especially, you MUST check if there is no problem in lowest power saving modes like L1.2 of PCIe and H8 of MPHY. | [5 empty] | 미진행
| Asynchronous F/F list (tcheck off F/F list) reviewed and implemented | 12.6 | The asynchronous flip-flop list should be described in the tcheck file by default. Generally, tcheck includes the followings. If not described, the simulation may be broken due to x-propagation. . 1st flip-flop of synchronizer . Stable input into flip-flop, but violation occurs . Other asynchronous conditions, which do not occur meta stable state. [Example] 1. Asynchronous flip-flops should be described in tcheck file as below.(e.g. nocheck.v) PATH top.u0_MPHY_TEST_TOP.I_CMN.u_term_tune.cmp_ff_reg -tcheck 2. Following command line option must be defined in verilog command line : +nctfile+"./nocheck.v" | [5 empty] | 미진행
13. ATPG (TetraMax) | Confirmed that test coverage should be at least 98% | 13.1 | Test coverage of stuck-at ATPG MUST be at least 98%. | [5 empty] | 미진행
14. PSI Analysis (RedHawk) | IR drop analysis report reviewed and clean | 14.1 | You MUST cross-check the weakness of design with physical design team, and designer should refer to sign-off document for each process. For each voltage corner, the worst static IR drop from bumps or pads to each instance MUST be lower than 3% * Vtyp. | [5 empty] | 미진행
| Dynamic voltage drop(DvD) analysis report reviewed and clean | 14.2 | You MUST cross-check the weakness of design with physical design team, and designer should refer to sign-off document for each process. For each voltage corner, the worst dynamic voltage drop from bumps or pads to each instance MUST be lower than the limits described in the sign-off document. Also, this analysis should be performed in function mode as well as scan mode. | [5 empty] | 미진행
| Electromigration(EM) analysis report reviewed and clean | 14.3 | To guarantee the reliability of the product, it is necessary to check EM and to fix the violated ones for both power and signal nets. You MUST cross-check the weakness of design with physical design team, and designer should refer to sign-off document for each process. You MUST fix power and signal routing of design continuously until it eliminates all the EM violations. | [5 empty] | 미진행
15. Deliverables - Verilog Model | Sub-block renamed with prefix(or postfix) | 15.1 | In the SOC(or ASIC) top point of view, the same block(or primitive cell) name may have been used in other IPs, so you MUST add prefix to all sub-block name so that you can have a unique name. | [5 empty] | 미진행
| Timescale checked | 15.2 | The malfunction may occur due to different timescales for each module, so please obtain analog verilog model from analog design team and check the timescale. | [5 empty] | 미진행
| Power-aware checker implemented | 15.3 | Depending on which power is turned on and off between VDDA(e.g. logic power 0.8v) and VDDH(e.g. logic power 1.8v) during PHY initialization, PHY operation can be affected. Therefore, the assertion checker(i.e. SVA) MUST be added so that the customer can automatically detect the power-up sequence that is contrary to the simulation. [Example] - ifdef PA_ASSERTIONS | [5 empty] | 미진행
| Initialization checker implemented | 15.4 | Ensure that the assertion checker(i.e. SVA) is inserted to check whether the sequence between the reset and APB programming is correct during PHY initialization. For example, in the input offset calibration, the operation starts when the CMN reset is de-asserted. If the CMN reset is not asserted during the initial APB programming, even if the CMN reset is toggled again after APB programming, the malfunction is caused. [Example] - ifdef PCIE_PHY_CHECKER and ifdef DELAY_FOR_STOP | [5 empty] | 미진행
| Power-down and reset checker implemented | 15.5 | When creating a vector for IDS/IDD current measurement, insert the assertion checker(i.e. SVA) to verify whether the enable or reset signal for the analog block is deassert or asserted. This is to reduce the ATE iteration time by checking the blocks that are not off in the powerdown mode at the simulation stage. | [5 empty] | 미진행
16. Deliverables - Library (PrimeTime, MakeLib (or Liberty Auto Generator)) | Library extracted with final netlist and SPEF | 16.1 | Timing liberty can be used in place of the block's netlist for timing analysis at a hierer level of the design hierarchy and the extracted model is an abstraction of the block interface timing behavior using sequential and combination timing arcs. Before you generate a timing model, ensure that final netlist contains no timing violations. | [5 empty] | 미진행
| set_input_transition for all inputs implemented | 16.2 | In addition to constraints such as clocks, exceptions, and case values, you should define data and clock signal arrival time ranges at the block inputs, data and clock signal transition ranges at the block inputs, and the external load ranges at the block outputs. Recommended I/O constraints for ETM extraction . Input transition time: min = 0.0 / max = 0.5 (e.g. set_input_transition 0.5 [all_inputs]) . Input delay: follow design budget | [5 empty] | 미진행
| set_max_transition for all outputs implemented | 16.3 | In addition to constraints such as clocks, exceptions, and case values, you should define data and clock signal arrival time ranges at the block inputs, data and clock signal transition ranges at the block inputs, and the external load ranges at the block outputs. Recommended I/O constraints for ETM extraction . Output max transition time: 0.5 (e.g. set_max_transition 0.5 [all_outputs]) | [5 empty] | 미진행
| set_max_capacitance for all outputs implemented | 16.4 | In addition to constraints such as clocks, exceptions, and case values, you should define data and clock signal arrival time ranges at the block inputs, data and clock signal transition ranges at the block inputs, and the external load ranges at the block outputs. Recommended I/O constraints for ETM extraction . Output max capacitance: (all outputs)max = 0.1, (PAD): max = 64 (e.g. set_max_capacitance 0.1 [all_outputs], set_max_capacitance 64 [get_ports $PAD_NAME]) - The default value is 0.1 pf. If the internal cap is large, the default value is adjusted. The CAP value of analog pads (DP, DN, and ATB) MUST be large enough to eliminate unnecessary violations. | [5 empty] | 미진행
| Pins with zero capacitance checked | 16.5 | Check whether there is a pin which has an unintended zero capacitance. - [Makelib] Check the file, 8_Report/64_fixed_cap_list.*.rpt file. | [5 empty] | 미진행
| All clock pins defined and reviewed | 16.6 | Make sure that all clock pins are defined. - [Makelib] Check the files, 8_Report/9_ parse_final_lib.$lib _ file.rpt & final.lib file. If necessary, check the file, 0_parse_raw_lib.$lib_file.rpt. | [5 empty] | 미진행
| All PAD pins defined and reviewed | 16.7 | Make sure that all PAD pins are defined. - [Makelib] Check the files, 8_Report/9_ parse_final_lib.$lib _ file.rpt & final.lib file. If necessary, check the file, 0_parse_raw_lib.$lib_file.rpt. | [5 empty] | 미진행
| no_timing arc pin list reviewed | 16.8 | Verify that no_timing arc list is correct. | [5 empty] | 미진행
| related_pin and timing arc of signals checked | 16.9 | Check whether the relation between related_pin and timing is defined correctly. - [Makelib] Check the files, 8_Report/9_ parse_final_lib.$lib _ file.rpt & final.lib file. If necessary, check the file, 0_parse_raw_lib.$lib_file.rpt. | [5 empty] | 미진행
| Internal clock transition checked | 16.10 | Make sure that transition for internal clock is defined. - [Makelib] Check the files, 8_Report/9_ parse_final_lib.$lib _ file.rpt & final.lib file. If necessary, check the file, 0_parse_raw_lib.$lib_file.rpt. | [5 empty] | 미진행
| Real capicitance value for all pins checked | 16.11 | In order to accurately describe the liberty, the RC values from the actual GDS MUST be described in the file. For this, there is a flow that reflects real capacity in the middle of creating a liberty. For example, if the input of A is described but the cap of the signal is too small, the buffer drive voltage of the path connected to this signal may be used very weakly, so the transition time of the signal may increase. Therefore, it is necessary to extract the correct capacity for the signal from the GDS of the entire PHY and apply it to the liberty generation flow. - [Makelib] Check the files, 8_Report/64_fixed_cap_list.*.rpt | [5 empty] | 미진행
| [for SEC_LIB only] No errors in Cubicware log | 16.12 | Error MUST be cleared. - [Makelib] Check the files, 8_Report/4_run_cubic.*.cubic_log/cubic_error | [5 empty] | 미진행
| No errors in Library-Compiler(or Design-Compiler) log | 16.13 | Error MUST be cleared. - [Makelib] Check the files, 8_Report/8_make_db.log | [5 empty] | 미진행
| SEC lib with correct naming convention | 16.14 | - 28nm and 14nm ; $TOP_CELL_NAME_$Library_family_$Process_$Voltage_$Temperature(_$Capacitance) [Example] HSI_DPHY_M4S4_TOP_ss20lpe_ff_1p050v_125c_cmax.lib - 10nm or later ; Refer to linked material | [5 empty] | 미진행
| Output clock defined from source clock(i.e. internal clock) | 16.15 | Verify that all output clocks have internal source clock as related clock. | [5 empty] | 미진행
| Top name, area, width and height matched with LEF | 16.16 | Top cell name, area, width and height decribed in liberty MUST be matched ones of LEF. | [5 empty] | 미진행
| pg_pin and related_power/ground_pin checked with analog design team | 16.17 | The liberty file has pin attributes, related_power_pin and related_ground_pin, to let the tools know how to connect tie signals to proper power and ground nets. Check if all pins are defined with correct related_power_pin and related_ground_pin. | [5 empty] | 미진행
| lib_checker's result checked | 16.18 | Verify all results of LIB checker with physical implemetation team. . Clock: pin name, clock source, timing table, internal clock . IO: pin name, clock source, timing table, direction . ETC: is_macro_cell flag | [5 empty] | 미진행
17. Deliverables - Vector(WGL) | Vectors are generated using vector generation script(i.e. vector_gen.py) | 17.1 | Vectors(i.e. WGL) MUST be generated using following vector generation scripts: . vector_gen.py and checker_gen.py | [5 empty] | 미진행
| SFR value reviewed with analog design team | 17.2 | If the final SFR value is not reflected on test vectors, this causes unnecessary iteration in the ATE test. During WGL generation, make sure that the final SFR value is finally confirmed by the analog design team. | [5 empty] | 미진행
| All wave dumps reviewed with analog design team | 17.3 | Before creating vectors, you MUST review the test sequence through the wave dumps, and check if each test sequence is correct. | [5 empty] | 미진행
| All WGL scenarios generated | 17.4 | Basically, it is necessary to check the test list once more and check if there are any test cases that have not been delivered to customer. Missing test cases may eventually fail to filter-out errors in test mode integrations from SOC(or ASIC). If there is a product that does not go through advanced MPW, it is necessary to discuss enough scenarios with analog design team, review simulation and check SFR setting. | [5 empty] | 미진행
| All test cases simulated with back-annotation | 17.5 | VTRAN translates ATE test program to verification testbenches. So, you MUST run the simulation with the testbench and verify the test vector thru re-simulation. [Note] Linked material is just a reference, not for sign-off. | [5 empty] | 미진행
| Floating input checked | 17.6 | All input test pins or clock pins that are not used for each IP MUST be fixed to LOW or HIGH, so leakage current generated by input floating should be prevented. | [5 empty] | 미진행
18. Deliverables - IP-XACT | Auto-mapped BUS(IO) interface checked | 18.1 | IP-XACT based connection review of PCS and PMA. If the blocks are automatically mapped according to the automatic BUS interface definition, they may be misconnected, so cross-check them with PCS design team. | [5 empty] | 미진행
19. Deliverables - JTAG wrapper | All test cases simulated with back-annotation | 19.1 | All test cases MUST be verified with JTAG wrapper to confirm signal flow in JTAG test mode. | [5 empty] | 미진행
20. Deliverables - Datasheet and Testplan | STA guide reviewed and described correctly | 20.1 | STA guide for all IP's clocks should be described in user guide(or data sheet) and you MUST check the timing relationship especially between internal clock and output clocks. | [5 empty] | 미진행
| Test guide reviewed and described correctly | 20.2 | Integration guide for test mode should be described in user guide(or data sheet) and following test modes MUST be included: . ATE . SCAN . HTOL . Vacation Mode(DVS) | [5 empty] | 미진행
| Power-up(initialization) sequence reviewed with analog design team | 20.3 | Make sure initialization sequence is described in data sheet and you should check carefully all sequence including power-up. | [5 empty] | 미진행
| Maximum APB clock frequency reviewed and described correctly | 20.4 | The confirmed maximum APB clock frequency MUST be specified in data sheet. | [5 empty] | 미진행
21. Metal Revision | Regression with CR and 100% passing | 21.1 | If there is a RTL fix after Final-DV, you MUST issue a change request(CR) to check if there is no side effect and request DV regression again to design verification team. | [5 empty] | 미진행
| ATPG re-run and scan vector regenerated | 21.2 | If netlist is changed after ATPG, you MUST run ATPG again with the updated netlist and release new scan vector. | [5 empty] | 미진행